## WBS Spreadsheet
Milestone | Task ID | Task | Owner | Duration (days) | Notes
Establish a plant delivery and logistics plan | 1.1 | Source packaging materials | Fulfillment Director | 20 | The Fulfillment Director sources materials
| 1.2 | Hire delivery drivers | Human Resources Specialist | 10 | The Human Resources Specialist oversees hiring
| 1.3 | Calculate the delivery fees | Financial Analyst | 2 | The Financial Analyst tracks costs and revenue
Select and install supply chain software and equipment | 2.1 | Supervise vendor setup of inventory management and fulfillment software | Inventory Manager | 5 | The Inventory Manager maintains inventory and coordinates with the Quality Assurance Tester to ensure software and equipment are installed and set up properly
| 2.2 | Supervise vendor installation of the fulfillment equipment | Inventory Manager | 5 | The Inventory Manager maintains inventory and coordinates with the Quality Assurance Tester to ensure software and equipment are installed and set up properly
| 2.3 | Determine internal safety protocols for the equipment | Quality Assurance Tester | 2 | The Quality Assurance Tester ensures product quality and determines safety protocols and best practices
Develop and launch an employee training program | 3.1 | Develop training sessions | Human Resources Specialist | 2 | The Human Resources Specialist develops the communication plan
| 3.2 | Train employees to use the software and equipment | Human Resources Specialist | 2 | The Human Resources Specialist oversees the Training Manager and sets up the training program
| 3.3 | Monitor employee progress and improve training processes | Training Manager | 14 | The Training Manager scedules and run the training program on the established protocols